## Budget
|  | Colchester Budget | [5 empty] | Date: 4.03.2024
Munis Acct. No. | Description | Original Budget Amount | Budget Adjustments | Referendum Adjustment | Current Budget | Expended (Invoiced) | Committed Encumbered | Uncommitted Balance | Total Project Cost | % Expended/ Completed
|  | a | b | c | d | e | f | g | h | i
[5 empty] | a + b + c |  |  | f - e | e + f | d / c
Architect and Engineering Services
30054780-62201 | A/E Fees | 450000 | -35000 | 35000 | 450000 | 395490.83 | 411621.49 | 38378.51 | 450000 | 87.89%
Owner's Oversight Fees
30054780-62250 | Project Manager/Owner's Rep. | 297000 | 18000 | 25000 | 340000 | 311465.18 | 338244.18 | 1755.82 | 340000 | 91.61%
30054780-62208 | Commissioning Agent | 12500 | -5000 | 7500 | 15000 | 0 | 0 | 15000 | 15000 | 0%
30054780-62208 | Testing and Inspections | 10000 | 15000 | 25000 | 50000 | 27142.25 | 27142.25 | 22857.75 | 50000 | 54.28%
Town Professional Fees
30054780-60302 | Town Legal Services | 5000 |  | 5000 | 10000 | 4372.5 | 4372.5 | 5627.5 | 10000 | 43.73%
30054780-61101 | Costs of Issuance | 178107 | -175000 | 94893 | 98000 | 0 | 0 | 98000 | 98000 | 0%
30054780-61206 | Town Insurance/Builder's Risk | 12500 | -12500 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-61105 | Administrative Costs | 12000 | -5000 |  | 7000 | 3640 | 3640 | 3360 | 7000 | 52%
30054780-61232 | Printing & Legal Notices | 8000 | -5000 |  | 3000 | 725.62 | 725.62 | 2274.38 | 3000 | 24.19%
Construction Costs
30054780-64469 | Construction Manager GMP | 7429465 | 1247005 | 498530 | 9175000 | 3345739.29 | 8953530.72 | 221469.28 | 8953530.72 | 36.47% | 338244.18
30054780-64469 | State Building Permit | 2017 | -2017 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-64469 | Utility Connection Fees | 15000 | 23923 | 36077 | 75000 | 63256.86 | 85046.68 | -10046.68 | 75000 | 84.34%
FF & E (Furniture, Fixtures, Equip.
30054780-68416 | Furniture and Equipment | 300000 | -300000 | 327000 | 327000 | 0 | 27869.49 | 299130.51 | 327000 | 0%
30054780-61263 | Moving & Relocation Costs | 20000 | -20000 | 25000 | 25000 | 0 | 0 | 25000 | 25000 | 0%
Contingencies
30054780-61411 | Design and Estimating Contingency | 324988 | -324988 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-61411 | Owner's Contingency | 423423 | -419423 | 421000 | 425000 | 0 | 0 | 425000 | 425000 | 0%
| Grand Totals | 9500000 | 0 | 1500000 | 11000000 | 4151832.53 | 9852192.93 | 1147807.07 | 11000000 | 37.74%
Pre Referendum Costs
| Silver/Petrucelli - Architects | 47000 | 0 |  | 47000 | 41352.08 | 46991 | 9 | 47000 | 87.98%
| Construction Solutions Group - OPM | 15000 | 0 |  | 15000 | 14798.65 | 14798.65 | 201.35 | 15000 | 98.66%
| Pre Referendum Totals | 62000 | 0 |  | 62000 | 56150.73 | 61789.65 | 210.35 | 62000 | 90.57%
COR's
Silver/Petrucelli |  | g: Pending
001 | Additional Test Bore Costs | a: 2022-03-08; f: 5472
002 | Additional Survey | a: 2022-06-17; f: 3300
003 | Wetlands Delineation/ Wetlands Report & Submission | a: 2022-06-17; f: 8030
004 | Soil Boring and Flow Test | a: 2022-06-17; f: 655.12
005 | Fee Adjustment | a: 2022-06-27; f: 485
006 | Printing Reimbursible | a: 2023-03-08; f: 2955.37
007 | Escalation Costs | a: 2023-03-28; f: 6600
Total |  | f: 27497.49
Construction Solutions Group |  | g: Pending
001 | Additional Cost Estimates | a: 2022-01-11; f: 15455
002 | Escalation Costs | a: 2023-05-09; f: 16770
003 | Additional Estimating Services | a: 2024-03-19; f: 1725
003 | Additional Clerk of the Works/ Site Coverage (1 month) | a: 2024-03-19; f: 22344.54
003 | Additional Clerk of the Works/ Site Coverage (pending) | a: Draft
Total |  | f: 56294.54
BRD Builders |  | g: Pending
001 | Siltsoxx - Credit | a: 2023-04-19; f: -3403.68
002 | Stone Trenches | a: 2023-05-09; f: 45270.52
003 | Foundation Building Code Upgardes | a: 2023-08-15; f: 18384.74
003 | Storefront Credit (CW-1 Elleptical) | a: 2023-08-15; f: -13136.46
004 | Conduit for future generator | a: 2023-10-04; f: 14346.35
005 | Electrical Building Code Upgrades | a: 2023-12-20; f: 3572.22
006 | Relocate underground electrical primaries and tel/ data | a: 2024-01-09; f: 25127.86
007 | Alt- Kitchen Equipment | a: 2024-01-31; f: 45000
007 | Alt- Wainscoting/ handrail | a: 2024-01-31; f: 25000
007 | Alt- Coffered Ceiling | a: 2024-01-31; f: 85000
008 | Knox Box | a: 2024-02-03; f: 893.55
| CCD #001 -Water Diversion | a: 2023-01-23; f: 64465.2
| Moment connection Modification | a: 2024-03-04; f: 5287.06
| Door Hardware Upgrades | a: 2024-02-22; f: 5275.73
| Retaining Wall Addition | a: 2024-03-21; f: 7447.63
| Water Connection Credit | a: 2023-01-15; g: -4086.81
| Cutain Drain Credit from CO 2 | a: 2023-11-30; g: -5774.76
| Demising Wall Dry Storage | a: 2023-12-21; g: TBD
| Spot Grades and Walk Changes | a: 2024-03-28; g: 9922.66
| Fire Alarm Stopper Covers (Credit) | a: 2024-03-15; g: -250.58
| Regrade Patio per SK-15. | a: 2024-03-28; g: 816.64
| Gas Line for Furture Generator | a: 2024-04-02; g: 5089.09
Total |  | f: 328530.72; g: 5716.24

## Payments- Inv
Firm Name | Date | Invoice Number | Description | Category | Amount
CSG |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 14798.65
CSG | 2021-03-04 | 1 | Pre-Construction Services | Pre Referendum Costs | 9000
CSG | 2021-06-07 | 2 | Pre-Construction Services | Pre Referendum Costs | 3000
CSG | 2021-07-23 | 3 | Pre-Construction Services | Pre Referendum Costs | 2798.65
|  |  |  | Total | 14798.65
CSG |  |  | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 338244.18 | 353042.83
CSG | 2022-03-01 | 4 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6880
CSG | 2022-04-01 | 5 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6000
CSG | 2022-05-01 | 6 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 14525
CSG | 2022-06-01 | 7 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 2000
CSG | 2022-07-03 | 7A | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 0
CSG | 2022-08-01 | 8 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 15132.69
CSG | 2022-11-30 | 9 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 3027.56
CSG | 2023-05-02 | 1a | Construction Services -CA | Project Manager/Owner's Rep. | 20819.99
CSG | 2023-06-06 | 2a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-07-07 | 3a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-08-02 | 4a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-09-01 | 5a | Construction Services -CA | Project Manager/Owner's Rep. | 22334.54
CSG | 2023-10-02 | 6a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-10-31 | 7a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-11-30 | 8a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-12-31 | 9a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-02-09 | 10a | Construction Services -CA | Project Manager/Owner's Rep. | 19644.54
CSG | 2024-03-01 | 11a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-04-01 | 12A | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
|  |  |  | Total | 311465.18
Committee Clerk |  |  | Administrative Costs | Administrative Costs | 0
Committee Clerk | 2021-12-14 | 1 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-01-25 | 2 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-08 | 3 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-22 | 4 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-08 | 5 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-29 | 6 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-12 | 7 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-26 | 8 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-10 | 9 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-24 | 10 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-14 | 11 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-28 | 12 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-12 | 13 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-26 | 14 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-01 | 15 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-09 | 16 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-23 | 17 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-09-13 | 18 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-19 | 19 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-25 | 20 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-11-22 | 21 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-12-01 | 22 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 23 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 24 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 25 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-12-13 | D- 011 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-01-10 | D- 012 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-01-24 | D- 013 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-02-14 | D- 014 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-02-28 | D- 015 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-03-28 | D- 016 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-04-04 | D- 017 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-04-11 | D- 018 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-05-09 | D- 019 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-05-23 | D- 020 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-06-13 | D- 021 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-07-11 | D- 022 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-08-22 | D- 023 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-09-12 | D- 024 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-09-19 | D- 025 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-09-26 | D- 026 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-10-10 | D- 027 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-10-24 | D- 028 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-11-15 | D- 029 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-11-19 | D- 030 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-11-29 | D- 031 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-12-12 | D- 032 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-01-09 | D- 033 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-01-23 | D- 034 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-01-31 | D- 035 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-02-01 | D- 036 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-02-13 | D- 037 | Administrative Costs | Administrative Costs | 70
|  |  |  | Total | 3640
Silver Petrucelli |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 46991
Silver Petrucelli | 2020-06-01 | 20-1473 | Silver/Petrucelli - Architects | Pre Referendum Costs | 9398
Silver Petrucelli | 2020-07-01 | 20-1694 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2020-08-01 | 20-1943 | Silver/Petrucelli - Architects | Pre Referendum Costs | 2349.55
Silver Petrucelli | 2020-09-01 | 20-2176 | Silver/Petrucelli - Architects | Pre Referendum Costs | 14097.3
Silver Petrucelli | 2020-10-01 | 20-2257 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2021-02-01 | 21-0420 | Silver/Petrucelli - Architects | Pre Referendum Costs | 1409.93
|  |  |  | Total | 41352.08
Silver Petrucelli |  |  | Architect and Engineering Services | A/E Fees | 384124
Silver Petrucelli | 2022-02-01 | 22-0125 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-02-01 | 22-0036 | Architect and Engineering Services | A/E Fees | 0
Silver Petrucelli | 2022-03-01 | 22-0208 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-04-01 | 22-0366 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-05-01 | 22-0432 | Architect and Engineering Services | A/E Fees | 7553
Silver Petrucelli | 2022-06-01 | 22-0537 | Architect and Engineering Services | A/E Fees | 48986.6
Silver Petrucelli | 2022-06-01 | 22-0637 | Architect and Engineering Services | A/E Fees | 11985.12
Silver Petrucelli | 2022-07-01 | 22-0703 | Architect and Engineering Services | A/E Fees | 42211.4
Silver Petrucelli | 2022-08-01 | 22-0905 | Architect and Engineering Services | A/E Fees | 20716.8
Silver Petrucelli | 2022-09-01 | 22-0987 | Architect and Engineering Services | A/E Fees | 5179.2
Silver Petrucelli | 2022-10-01 | 22-1157 | Architect and Engineering Services | A/E Fees | 17264
Silver Petrucelli | 2022-11-01 | 22-1283 | Architect and Engineering Services | A/E Fees | 4316
Silver Petrucelli | 2023-02-01 | 22-0232 | Architect and Engineering Services | A/E Fees | 1079
Silver Petrucelli | 2023-02-01 | 22-0281 | Architect and Engineering Services | A/E Fees | 2955.37
Silver Petrucelli | 2023-03-01 | 23-166 | Architect and Engineering Services | A/E Fees | 1079
Silver Petrucelli | 2023-04-01 | 23-224 | Architect and Engineering Services | A/E Fees | 11995
Silver Petrucelli | 2023-05-01 | 23-403 | Architect and Engineering Services | A/E Fees | 7553
Silver Petrucelli | 2023-06-01 | 23-557 | Architect and Engineering Services | A/E Fees | 6474
Silver Petrucelli | 2023-07-01 | 23-678 | Architect and Engineering Services | A/E Fees | 10790
Silver Petrucelli | 2023-08-01 | 23-925 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2023-09-01 | 23-1108 | Architect and Engineering Services | A/E Fees | 5449.34
Silver Petrucelli | 2023-10-01 | 23-1188 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2023-11-01 | 23-1409 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2023-12-01 | 23-1532 | Architect and Engineering Services | A/E Fees | 10790
Silver Petrucelli | 2024-01-15 | 24-131 | Architect and Engineering Services | A/E Fees | 10790
Silver Petrucelli | 2024-02-01 | 24-230 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2024-03-01 | 24-249 | Architect and Engineering Services | A/E Fees | 10790
|  |  |  | Total | 395490.83
|  |  | Printing & Legal Notices | Printing & Legal Notices
Rivereast News Bulletin | 2022-09-07 | 217798-001RE | Printing & Legal Notices | Printing & Legal Notices | 220
Hartford Courant | 2022-09-11 | 60181913000 | Printing & Legal Notices | Printing & Legal Notices | 505.62
|  |  |  | Total | 725.62
|  |  | Town Legal Services | Town Legal Service
Shipman & Goodwin | 2022-02-16 | 1213 | Town Legal Service | Town Legal Service | 940.5
Shipman & Goodwin | 2024-01-31 | NA | Town Legal Service | Town Legal Service | 1628
DECD | 2024-03-01 | NA | DECD Legal Fees | Town Legal Service | 1804
|  |  |  | Total | 4372.5
|  |  | Construction Costs | Construction Manager GMP | 8953530.72
BRD Builders | 2023-03-31 | 1 | Construction Manager GMP | Construction Manager GMP | 182299.77
BRD Builders | 2023-04-30 | 2 | Construction Manager GMP | Construction Manager GMP | 125059.73
BRD Builders | 2023-05-31 | 3 | Construction Manager GMP | Construction Manager GMP | 175505.19
BRD Builders | 2023-06-30 | 4 | Construction Manager GMP | Construction Manager GMP | 148812.75
BRD Builders | 2023-07-31 | 5 | Construction Manager GMP | Construction Manager GMP | 195315.77
BRD Builders | 2023-08-31 | 6 | Construction Manager GMP | Construction Manager GMP | 163575.52
BRD Builders | 2023-09-30 | 7 | Construction Manager GMP | Construction Manager GMP | 150772.51
BRD Builders | 2023-10-31 | 8 | Construction Manager GMP | Construction Manager GMP | 264337.5
BRD Builders | 2023-11-30 | 9 | Construction Manager GMP | Construction Manager GMP | 397627.39
BRD Builders | 2023-12-31 | 10 | Construction Manager GMP | Construction Manager GMP | 671459.95
BRD Builders | 2024-01-31 | 11 | Construction Manager GMP | Construction Manager GMP | 442693.82
BRD Builders | 2024-02-29 | 12 | Construction Manager GMP | Construction Manager GMP | 428279.39
BRD Builders | 2024-03-31 | 13 | Construction Manager GMP | Construction Manager GMP | In Review
|  |  |  | Total | 3345739.29
|  |  | Owner's Oversight Fees | Testing and Inspections | 50000
IMTL | 2023-05-01 | 5836-A | Owner's Oversight Fees | Testing and Inspections | 1069
IMTL | 2023-06-01 | 5836-B | Owner's Oversight Fees | Testing and Inspections | 4329
IMTL | 2023-07-01 | 5836-C | Owner's Oversight Fees | Testing and Inspections | 5379.94
IMTL | 2023-08-02 | 5836-D | Owner's Oversight Fees | Testing and Inspections | 5555.5
IMTL | 2023-08-07 | 5837-A | Owner's Oversight Fees | Testing and Inspections | 437.5
IMTL | 2023-08-14 | 5837-B | Owner's Oversight Fees | Testing and Inspections | 812.5
IMTL | 2023-09-18 | 5836-E | Owner's Oversight Fees | Testing and Inspections | 1945
IMTL | 2023-09-19 | 5837-C | Owner's Oversight Fees | Testing and Inspections | 500
IMTL | 2023-10-09 | 5826-F (Rev) | Owner's Oversight Fees | Testing and Inspections | 1432
IMTL | 2023-11-17 | 5836-G | Owner's Oversight Fees | Testing and Inspections | 1976.81
IMTL | 2023-11-06 | 5837-D | Owner's Oversight Fees | Testing and Inspections | 500
IMTL | 2023-11-14 | 5837-E | Owner's Oversight Fees | Testing and Inspections | 375
IMTL | 2023-12-14 | 5837-F | Owner's Oversight Fees | Testing and Inspections | 562.5
IMTL | 2024-12-19 | 5836-H | Owner's Oversight Fees | Testing and Inspections | 842
IMTL | 2024-01-11 | 5836-I | Owner's Oversight Fees | Testing and Inspections | 246
IMTL | 2024-01-17 | 5837-G | Owner's Oversight Fees | Testing and Inspections | 687.5
IMTL | 2024-02-06 | 5836-J | Owner's Oversight Fees | Testing and Inspections | 246
IMTL | 2024-03-07 | 5836-K | Owner's Oversight Fees | Testing and Inspections | 246
|  |  |  | Total | 27142.25
|  |  | Construction Costs | Utility Connection Fees | 75000
Eversource (Gas) | 2023-08-23 |  | Gas Service | Utility Connection Fees | 38705.5
Eversource (Electric) | 2023-11-27 |  | Electric Service | Utility Connection Fees | 7091.26
Colchesetr Water Department | 2023-11-01 |  | Water Connection Fee | Utility Connection Fees | 14460.1
Dutch Associates | 2023-11-01 |  | Easement Documentation | Utility Connection Fees | 3000
|  |  | Construction Costs | Utility Connection Fees | 21789.82
Sertex | 2024-03-05 | Quote dated 3.5.24 |  | Utility Connection Fees
|  |  |  | Total | 63256.86
FF & E (Furniture, Fixtures, Equip.
|  |  |  | FFE Total Committed Cost | 27869.49
Novus | 2024-02-22 | Quote #6254 | Novus Computer Purchase | Furniture and Equipment
Novus | 2024-03-05 | Quote #6285 | Novus Telephone Purchase | Furniture and Equipment
Novus | 2024-03-06 | Quote #6269 | Novus Construction Proposal | Furniture and Equipment
|  |  |  | Page Total | 4207983.26
|  |  |  | Buget Total | 4207983.26
|  |  |  | Check | 0

## Tranfers-Adj
Date | Budget Category | Description | Category | Amount
2022-01-11 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -1000
2022-12-01 | Owner's Contingency | Move $$ from Owner's Contingency to GMP | Budget Adjustment | -200000
2023-01-10 | Owner's Contingency | Move $$ from Owner's Contingency to GMP | Budget Adjustment | -200000
2023-08-22 | Owner's Contingency | Move $$ from Owner's Contingency to Utility Connection Fees | Budget Adjustment | -18423
| Owner's Contingency |  | Total = | -419423
2022-01-11 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 1000
2023-05-09 | Project Manager/Owner's Rep. | $ Utility Conncetion Fee to Project Manager/ Owner Rep | b | 17000
| Project Manager/Owner's Rep. |  | Total = | 18000
2022-12-01 | Design and Estimating Contingency | Deduct Value/ Move to Utility Connection Fees | Budget Adjustment | -107500
2022-12-01 | Design and Estimating Contingency | Deduct Value/ Move to Construction Manager GMP | Budget Adjustment | -217488
| Design and Estimating Contingency |  | Total = | -324988
2022-10-12 | Utility Connection Fees | Increase value based on BC meeting 10/11/20222 | Budget Adjustment | 107500
2023-01-10 | Utility Connection Fees | Tranfer value to Construction Manager GMP | Budget Adjustment | -40000
2023-03-28 | Utility Connection Fees | Transfer value to AE Fees | Budget Adjustment | -5000
2023-05-09 | Utility Connection Fees | Transfer to Project Manager/ Owner Rep | Budget Adjustment | -17000
2023-05-23 | Utility Connection Fees | Tranfer value to Construction Manager GMP | Budget Adjustment | -40000
2023-08-22 | Utility Connection Fees | Tranfer value from Owner's Contingency | Budget Adjustment | 18423
| Utility Connection Fees |  | Total = | 23923
2022-12-01 | Construction Manager GMP | Move remaining value from Design and Estimating Contingency per BC meeting on 10/11/2022 | Budget Adjustment | 217488
2022-12-01 | Construction Manager GMP | Move $$ from State Building Permit | Budget Adjustment | 2017
2022-12-01 | Construction Manager GMP | Value tranferred from Town Insurance/ BR | Budget Adjustment | 12500
2022-12-01 | Construction Manager GMP | Value tranferred from FFE | Budget Adjustment | 200000
2022-12-01 | Construction Manager GMP | Value transferred from Owner Contingency | Budget Adjustment | 200000
2023-01-10 | Construction Manager GMP | Value transferred from AE Fees | Budget Adjustment | 40000
2023-01-10 | Construction Manager GMP | Value transferred from Cost of Insurnace | Budget Adjustment | 175000
2023-01-10 | Construction Manager GMP | Value transferred from Admin Costs | Budget Adjustment | 5000
2023-01-10 | Construction Manager GMP | Value transferred from Printing and Legal Notices | Budget Adjustment | 5000
2023-01-10 | Construction Manager GMP | Value transferred from Utility Connection Fees | Budget Adjustment | 40000
2023-01-10 | Construction Manager GMP | Value transferred from Furniture and Equipment | Budget Adjustment | 90000
2023-01-10 | Construction Manager GMP | Value transferred from Moving and Relocation | Budget Adjustment | 15000
2023-01-10 | Construction Manager GMP | Value transferred from Owner Contingency | Budget Adjustment | 200000
2023-05-23 | Construction Manager GMP | Value transferred from Utility Connection Fees | Budget Adjustment | 40000
2023-08-08 | Construction Manager GMP | Value transferred from Moving and Relocation | Budget Adjustment | 5000
| Construction Manager GMP |  | Total = | 1247005
2022-12-01 | State Building Permit | Remove Value/ Move to GMP | Budget Adjustment | -2017
| State Building Permit |  | Total= | -2017
2022-12-12 | Town Insurance/Builder's Risk | Remove Value/ Move to GMP | Budget Adjustment | -12500
| Town Insurance/Builder's Risk |  | Total= | -12500
2022-12-01 | FFE | Remove Value/ Move to GMP | Budget Adjustment | -200000
2023-01-10 | FFE | Remove Value | Budget Adjustment | -90000
2023-07-11 | FFE | Remove Value/ Move to Testing and Inspections | Budget Adjustment | -10000
| FFE |  | Total= | -300000
2023-07-11 | Testing and Inspections | $ Add Value/ Move from FFE | Budget Adjustment | 10000
2023-10-10 | Testing and Inspections | $ Add Value/ Move from Commisioning Agent |  | 5000
| Testing and Inspections |  | Total= | 15000
2023-01-10 | Architect and Engineering Services | $ from AE Fees to Construction Manager GMP | Budget Adjustment | -40000
2023-03-28 | Architect and Engineering Services | Add Value/ Move from Utility Connection fee | Budget Adjustment | 5000
| Architect and Engineering Services |  | Total= | -35000
2023-01-10 | Town Professional Fees | $ from Cost of Insurance to Construction Manager GMP | Budget Adjustment | -175000
| Town Professional Fees |  | Total= | -175000
2023-01-10 | Town Professional Fees | $ from Admin Costs to Concstructoon Manager GMP | Budget Adjustment | -5000
| Town Professional Fees |  | Total= | -5000
2023-01-10 | Town Professional Fees | $ from Printing and Leagl Notices to Construction Manager GMP | Budget Adjustment | -5000
| Town Professional Fees |  | Total= | -5000
2023-01-10 | FF & E (Furniture, Fixtures, Equip. | $ from Moving and Relocation Costs to Construction Manager GMP | Budget Adjustment | -15000
2023-08-08 | FF & E (Furniture, Fixtures, Equip. | $ from Moving and Relocation Costs to Construction Manager GMP | Budget Adjustment | -5000
| FF & E (Furniture, Fixtures, Equip. |  | Total= | -20000
2023-10-10 | Commisioning Agent | $ from Commisioning Agent to Testing and Inspections | Budget Adjustment | -5000
| Commisioning Agent |  | Total= | -5000
|  |  | Math Check | 0