## Budget
|  | Colchester Budget | [5 empty] | 2026-05-12
Munis Acct. No. | Description | Original Budget Amount | Budget Adjustments | Referendum Adjustment | Current Budget | Expended (Invoiced) | Committed Encumbered | Uncommitted Balance | Total Project Cost | % Expended/ Completed
|  | a | b | c | d | e | f | g | h | i
[5 empty] | a + b + c |  |  | d - f | f + g | d / c
Architect and Engineering Services
30054780-62201 | A/E Fees | 450000 | -8715.18 | 35000 | 476284.82 | 471042.93 | 471042.93 | 5241.89 | 476284.82 | 98.9% | 0
Owner's Oversight Fees
30054780-62250 | Project Manager/Owner's Rep. | 297000 | 177507.84 | 25000 | 499507.84 | 499507.84 | 499507.84 | 0 | 499507.84 | 100% | 0
30054780-62208 | Commissioning Agent | 12500 | 6600 | 7500 | 26600 | 26600 | 26600 | 0 | 26600 | 100%
30054780-62208 | Testing and Inspections | 10000 | 5000 | 25000 | 40000 | 36301.25 | 36301.25 | 3698.75 | 40000 | 90.75%
Town Professional Fees
30054780-60302 | Town Legal Services | 5000 | 25000 | 5000 | 35000 | 34900.5 | 34900.5 | 99.5 | 35000 | 99.72%
30054780-61101 | Costs of Issuance | 178107 | -255000 | 94893 | 18000 | 12733.4 | 12733.4 | 5266.6 | 18000 | 70.74%
30054780-61206 | Town Insurance/Builder's Risk | 12500 | -12500 |  | 0 | 0 | 0 | 0 | 0 | 100%
30054780-61105 | Administrative Costs | 12000 | -5000 |  | 7000 | 5520 | 5520 | 1480 | 7000 | 78.86%
30054780-61232 | Printing & Legal Notices | 8000 | -5000 |  | 3000 | 1055.62 | 1055.62 | 1944.38 | 3000 | 35.19%
Construction Costs
30054780-64469 | Construction Manager GMP | 7429465 | 1467005 | 498530 | 9395000 | 9133826.41 | 9394309.15 | 690.85 | 9395000 | 97.22%
30054780-64469 | State Building Permit | 2017 | -2017 |  | 0 | 0 | 0 | 0 | 0 | 100%
30054780-64469 | Utility Connection Fees | 15000 | 30184.86 | 36077 | 81261.86 | 81261.86 | 81261.86 | 0 | 81261.86 | 100%
FF & E (Furniture, Fixtures, Equip.
30054780-68416 | Furniture and Equipment | 300000 | -252999.42 | 327000 | 374000.58 | 3736965.2 | 373965.2 | 35.38 | 374000.58 | 999.2%
30054780-61263 | Moving & Relocation Costs | 20000 | -41657.83 | 25000 | 3342.17 | 3342.17 | 3342.17 | 0 | 3342.17 | 100%
Contingencies
30054780-61411 | Design and Estimating Contingency | 324988 | -324988 |  | 0 | 0 | 0 | 0 | 0 | 100%
30054780-61411 | Owner's Contingency | 423423 | -803420.27 | 421000 | 41002.73 | 0 | 0 | 41002.73 | 41002.73 | 90.19%
| Grand Totals | 9500000 | 0 | 1500000 | 11000000 | 14043057.18 | 10940539.92 | 59460.08 | 11000000 | 127.7%
Pre Referendum Costs
| Silver/Petrucelli - Architects | 47000 | 0 |  | 47000 | 46991.2 | 46991 | 9 | 47000 | 99.98%
| Construction Solutions Group - OPM | 15000 | 0 |  | 15000 | 14798.65 | 14798.65 | 201.35 | 15000 | 98.66%
| Pre Referendum Totals | 62000 | 0 |  | 62000 | 61789.85 | 61789.65 | 210.35 | 62000 | 99.66%
COR's
Silver/Petrucelli |  | g: Pending
001 | Additional Test Bore Costs | a: 2022-03-08; f: 5472
002 | Additional Survey | a: 2022-06-17; f: 3300
003 | Wetlands Delineation/ Wetlands Report & Submission | a: 2022-06-17; f: 8030
004 | Soil Boring and Flow Test | a: 2022-06-17; f: 655.12
005 | Fee Adjustment | a: 2022-06-27; f: 485
006 | Printing Reimbursible | a: 2023-03-08; f: 2955.37
007 | Escalation Costs | a: 2023-03-28; f: 6600
008 | Additional Services to review soil conditions | a: 2024-04-15; f: 4455
009 | Additional CA Services for October 2024 | a: 2024-11-07; f: 6212.75
010 | Additional Services | a: 2024-12-10; f: 12169.75
011 | Mediation Costs & Addditional Services | a: 2025-02-11; f: 15397.5
012 | Additional CA Services for Feb. 2025 | a: 2025-05-13; f: 6025.1
013 | Additional CA Services for March 2025 | a: 2025-05-13; f: 335.75
014 | Additional CA Services for Nov. & Dec. 2024 | a: 2025-05-13; f: 5006.74
015 | Additional CA Services for April & May 2025 | a: 2025-06-17; f: 2666
016 | Additional CA Services for June 2025 | a: 2025-05-08; f: 1487
017 | Additional CA Services for July 2025 | a: 2025-08-01; f: 1163.6
018 | Additional CA Services for August 2025 | a: 2025-09-09; f: 3139.25
019 | Additional CA Services for September 2025 | a: 2025-10-08; f: 885
020 | Additional CA Services & SLR - TBD | f: 0
021 | Additional CA Services for Feb. 2026 | a: 2026-03-01; f: 203.5
022 | Additional CA Services for March 2026 | a: 2026-04-01; f: 274.5
Total |  | f: 86918.93
Construction Solutions Group |  | g: Pending
001 | Additional Cost Estimates | a: 2022-01-11; f: 15455
002 | Escalation Costs | a: 2023-05-09; f: 16770
003 | Additional Estimating Services | a: 2024-03-19; f: 1725
003 | Additional Clerk of the Works/ Site Coverage (1 month -April) | a: 2024-03-19; f: 22344.54
004 | Additional Clerk of the Works/ Site Coverage (1 month -May) | a: 2024-05-15; f: 22344.54
005 | Additional Clerk of the Works/ Site Coverage (1 month -June) | a: 2024-06-01; f: 22344.54
006 | Additional Clerk of the Works/ Site Coverage (1 month -July) | a: 2024-07-05; f: 22344.54
007 | Additional Clerk of the Works/ Site Coverage (1 month -August) | a: 2024-08-01; f: 22344.54
008 | Additional Clerk of the Works/ Site Coverage (1 month -September) | a: 2024-09-01; f: 22344.54
009 | Additional Clerk of the Works/ Site Coverage (1 month -October) | a: 2024-10-01; f: 22344.54
010 | Additional Clerk of the Works/ Site Coverage (1 month -November) | a: 2024-11-12; f: 15097.27
| Credit - Town Hall Roof Coverage | f: -2700
Total |  | f: 202759.05
BRD Builders |  | g: Pending
001 | Siltsoxx - Credit | a: 2023-04-19; f: -3403.07
002 | Stone Trenches | a: 2023-05-09; f: 45270.52
003 | Foundation Building Code Upgardes | a: 2023-08-15; f: 18384.74
003 | Storefront Credit (CW-1 Elleptical) | a: 2023-08-15; f: -13136.46
004 | Conduit for future generator | a: 2023-10-04; f: 14346.35
005 | Electrical Building Code Upgrades | a: 2023-12-20; f: 3572.22
006 | Relocate underground electrical primaries and tel/ data | a: 2024-01-09; f: 25127.86
007 | Alt- Kitchen Equipment | a: 2024-01-31; f: 45000
007 | Alt- Wainscoting/ handrail | a: 2024-01-31; f: 25000
007 | Alt- Coffered Ceiling | a: 2024-01-31; f: 85000
008 | Knox Box | a: 2024-02-03; f: 893.55
009 | Retaining Wall Addition | a: 2024-03-21; f: 7447.63
010 | Structural Steel Modifications | a: 2024-03-04; f: 5287.06
011 | Door Hardware Upgrades | a: 2024-02-22; f: 5275.73
012 | Patio Regrade | a: 2024-03-28; f: 816.64
013 | Fire Hydrant Credit | a: 2024-03-28; f: -910.28
014 | Not Issued Yet
015 | Roof Venting | a: 2024-04-17; f: 6718.37
016 | Masonry Window and Lintel Modifications | a: 2024-04-17; f: 2668.95
017 | Thermal Break Angle Iron Support | a: 2024-04-18; f: 2872.03
018 | Gas Line for Furture Generator | a: 2024-04-19; f: 4614.17
019 | Spot Grades and Walk Changes | a: 2024-05-09; f: 3496.46
020 | Demising wall between office 134 and 135 | a: 2024-05-09; f: 3639.49
021 | Annunciator Panel Credit | a: 2024-07-09; f: -595.9
022 | Cast Iron to PVC Waste Credit | a: 2024-04-25; f: -17849.51
023 | Gravity Hoods and Moterized Damper | a: 2024-05-06; f: 1310.83
024 | New Plantings at Louis Lane | a: 2024-11-14; f: 8909.05
025 | CCTV Cameras | a: 2024-11-14; f: 8329.67
026 | Cellular Dialer for Fire Alarm | a: 2024-11-14; f: 1343.86
027 | Added Lite for Kitchen Door | a: 2024-01-13; f: 287.5
028 | Added door closers to 6 doors (PCO 57) | a: 2024-12-16; f: 3396.66
029 | Credit Conference Room Data Outlet | a: 2025-03-11; f: -2000
030 | Credit - Accounting Reconciliation | a: 2025-03-11; f: -0.61
031 | Add Trap Seals to Kitchen Drains - 2 | a: 2025-04-08; f: 614.69
032 | Add Decorative Rock and Rip Rap Swale | a: 2025-06-17; f: 13115.75
CCD - 01 | Water Diversion | f: 64465.2
033 | Open PCO's | a: 2025-10-22; f: 400000
TOTAL
| Water Connection Credit | a: 2023-01-15; g: -4086.81
| Cutain Drain Credit from CO 2 | a: 2023-11-30; g: -5774.76
| SKC -17 Grade Chages Revised 8.1.2024 | a: 2024-08-21; g: 23447.07
| SKC -19 dated 8.12.2024 side walk changes | a: 8.21.2024; g: TBD
| Eliminate Section of Town Hall Parking, Add fill and topsoil | a: 2024-08-23; g: 1075.3
|  | 2024-06-20 | [5 empty] | TBD
Total |  | f: 769309.15; g: 14660.8
Total Fitness |  | g: Pending
001 | Second Elliptical Machine Credit | a: 2024-09-24; f: -4700
Total |  | f: -4700
Meyer Inc.
001 | Materials for relocation | a: 2025-01-14; f: 387.17
Total |  | f: 387.17
Sign Stop
001 | Computer Program Formatting | a: 2025-02-11; f: 200
Total |  | f: 200

## Payments- Inv
Firm Name | Date | Invoice Number | Description | Category | Amount
CSG |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 14798.65
CSG | 2021-03-04 | 1 | Pre-Construction Services | Pre Referendum Costs | 9000
CSG | 2021-06-07 | 2 | Pre-Construction Services | Pre Referendum Costs | 3000
CSG | 2021-07-23 | 3 | Pre-Construction Services | Pre Referendum Costs | 2798.65
|  |  |  | Total | 14798.65
CSG |  |  | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 0
CSG | 2022-03-01 | 4 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6880
CSG | 2022-04-01 | 5 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6000
CSG | 2022-05-01 | 6 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 14525
CSG | 2022-06-01 | 7 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 2000
CSG | 2022-07-03 | 7A | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 0
CSG | 2022-08-01 | 8 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 15132.69
CSG | 2022-11-30 | 9 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 3037.02
CSG | 2023-05-02 | 1a | Construction Services -CA | Project Manager/Owner's Rep. | 20819.99
CSG | 2023-06-06 | 2a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-07-07 | 3a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-08-02 | 4a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-09-01 | 5a | Construction Services -CA | Project Manager/Owner's Rep. | 22334.54
CSG | 2023-10-02 | 6a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-10-31 | 7a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-11-30 | 8a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-12-31 | 9a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-02-09 | 10a | Construction Services -CA | Project Manager/Owner's Rep. | 19644.54
CSG | 2024-03-01 | 11a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-04-01 | 12A | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-05-01 | 13A | Construction Services -CA | Project Manager/Owner's Rep. | 24069.54
CSG | 2024-06-01 | 14A | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-07-01 | 15A | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-09-04 | 16A | Construction Services -CA | Project Manager/Owner's Rep. | 44689.08
CSG | 2024-10-02 | 17A | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-11-05 | 18 | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2024-12-10 | 19 | Construction Services -CA | Project Manager/Owner's Rep. | 15097.27
|  |  |  | Total | 484708.69
Committee Clerk |  |  | Administrative Costs | Administrative Costs | 0
Committee Clerk | 2021-12-14 | 1 | Administrative Costs | Administrative Costs | 60
Committee Clerk | 2022-01-25 | 2 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-08 | 3 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-22 | 4 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-08 | 5 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-29 | 6 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-12 | 7 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-26 | 8 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-10 | 9 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-24 | 10 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-14 | 11 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-28 | 12 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-12 | 13 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-26 | 14 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-01 | 15 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-09 | 16 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-23 | 17 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-09-13 | 18 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-19 | 19 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-25 | 20 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-11-22 | 21 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-12-01 | 22 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 23 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 24 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 25 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-12-13 | D- 011 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-01-10 | D- 012 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-01-24 | D- 013 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-02-14 | D- 014 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-02-28 | D- 015 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-03-28 | D- 016 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-04-04 | D- 017 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-04-11 | D- 018 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-05-09 | D- 019 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-05-23 | D- 020 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-06-13 | D- 021 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-07-11 | D- 022 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-08-22 | D- 023 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-09-12 | D- 024 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-09-19 | D- 025 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-09-26 | D- 026 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-10-10 | D- 027 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-10-24 | D- 028 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-11-15 | D- 029 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-11-19 | D- 030 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-11-29 | D- 031 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-12-12 | D- 032 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-01-09 | D- 033 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-01-23 | D- 034 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-01-31 | D- 035 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-02-01 | D- 036 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-02-13 | D- 037 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-03-12 | D- 038 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-03-26 | D- 039 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-04-09 | D- 040 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-04-23 | D- 041 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-05-15 | D- 042 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-05-28 | D- 043 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2024-06-11 | D- 044 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 7/09/24 - 10/09/24 |  | Administrative Costs | Administrative Costs | 420
|  |  |  | Total | 4540
Silver Petrucelli |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 46991
Silver Petrucelli | 2020-06-01 | 20-1473 | Silver/Petrucelli - Architects | Pre Referendum Costs | 9398.2
Silver Petrucelli | 2020-07-01 | 20-1694 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2020-08-01 | 20-1943 | Silver/Petrucelli - Architects | Pre Referendum Costs | 2349.55
Silver Petrucelli | 2020-09-01 | 20-2176 | Silver/Petrucelli - Architects | Pre Referendum Costs | 14097.3
Silver Petrucelli | 2020-10-01 | 20-2257 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2021-02-01 | 21-0420 | Silver/Petrucelli - Architects | Pre Referendum Costs | 1409.93
Silver Petrucelli | 2024-07-01 | 24-788 | Silver/Petrucelli - Architects | Pre Referendum Costs | 5638.92
|  |  |  | Total | 46991.2
Silver Petrucelli |  |  | Architect and Engineering Services | A/E Fees | 384124
Silver Petrucelli | 2022-02-01 | 22-0125 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-02-01 | 22-0036 | Architect and Engineering Services | A/E Fees | 0
Silver Petrucelli | 2022-03-01 | 22-0208 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-04-01 | 22-0366 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-05-01 | 22-0432 | Architect and Engineering Services | A/E Fees | 7553
Silver Petrucelli | 2022-06-01 | 22-0537 | Architect and Engineering Services | A/E Fees | 48986.6
Silver Petrucelli | 2022-06-01 | 22-0637 | Architect and Engineering Services | A/E Fees | 11985.12
Silver Petrucelli | 2022-07-01 | 22-0703 | Architect and Engineering Services | A/E Fees | 42211.4
Silver Petrucelli | 2022-08-01 | 22-0905 | Architect and Engineering Services | A/E Fees | 20716.8
Silver Petrucelli | 2022-09-01 | 22-0987 | Architect and Engineering Services | A/E Fees | 5179.2
Silver Petrucelli | 2022-10-01 | 22-1157 | Architect and Engineering Services | A/E Fees | 17264
Silver Petrucelli | 2022-11-01 | 22-1283 | Architect and Engineering Services | A/E Fees | 4316
Silver Petrucelli | 2023-02-01 | 22-0232 | Architect and Engineering Services | A/E Fees | 1079
Silver Petrucelli | 2023-02-01 | 22-0281 | Architect and Engineering Services | A/E Fees | 2955.37
Silver Petrucelli | 2023-03-01 | 23-166 | Architect and Engineering Services | A/E Fees | 1079
Silver Petrucelli | 2023-04-01 | 23-224 | Architect and Engineering Services | A/E Fees | 11995
Silver Petrucelli | 2023-05-01 | 23-403 | Architect and Engineering Services | A/E Fees | 7553
Silver Petrucelli | 2023-06-01 | 23-557 | Architect and Engineering Services | A/E Fees | 6474
Silver Petrucelli | 2023-07-01 | 23-678 | Architect and Engineering Services | A/E Fees | 10790
Silver Petrucelli | 2023-08-01 | 23-925 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2023-09-01 | 23-1108 | Architect and Engineering Services | A/E Fees | 5449.34
Silver Petrucelli | 2023-10-01 | 23-1188 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2023-11-01 | 23-1409 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2023-12-01 | 23-1532 | Architect and Engineering Services | A/E Fees | 10790
Silver Petrucelli | 2024-01-15 | 24-131 | Architect and Engineering Services | A/E Fees | 10790
Silver Petrucelli | 2024-02-01 | 24-230 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2024-03-01 | 24-249 | Architect and Engineering Services | A/E Fees | 10790
Silver Petrucelli | 2024-04-01 | 24-413 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2024-04-25 | 24-462 | Architect and Engineering Services | A/E Fees | 4455
Silver Petrucelli | 2024-05-01 | 24-551 | Architect and Engineering Services | A/E Fees | 5395
Silver Petrucelli | 2024-06-01 | 24-638 | Architect and Engineering Services | A/E Fees | 3237
Silver Petrucelli | 2024-07-01 | 24-799 | Architect and Engineering Services | A/E Fees | 1079
Silver Petrucelli | 2024-09-01 | 24-1033 | Architect and Engineering Services | A/E Fees | 539.5
Silver Petrucelli | 2024-11-01 | 24-1297 | Architect and Engineering Services | A/E Fees | 6212.75
Silver Petrucelli | 2024-12-10 | 24-1441 | Architect and Engineering Services | A/E Fees | 12169.75
|  |  |  | Total | 433973.83
|  |  | Printing & Legal Notices | Printing & Legal Notices
Rivereast News Bulletin | 2022-09-07 | 217798-001RE | Printing & Legal Notices | Printing & Legal Notices | 220
Hartford Courant | 2022-09-11 | 60181913000 | Printing & Legal Notices | Printing & Legal Notices | 505.62
The Glastonbury Citizen | 2024-04-26 | 231735 | Printing & Legal Notices | Printing & Legal Notices | 121
The Glastonbury Citizen | 2024-05-10 | 2326360 | Printing & Legal Notices | Printing & Legal Notices | 99
The Glastonbury Citizen | 2024-06-14 | 235131 | Printing & Legal Notices | Printing & Legal Notices | 110
|  |  |  | Total | 1055.62
|  |  | Town Legal Services | Town Legal Service
Shipman & Goodwin | 2022-02-16 | 1213 | Town Legal Service | Town Legal Service | 940.5
Shipman & Goodwin | 2024-01-31 | NA | Town Legal Service | Town Legal Service | 1628
DECD | 2024-03-01 | NA | DECD Legal Fees | Town Legal Service | 1804
American Arbitration Association | 2024-03-21 | Case # 01-24-0000-5233-2-AA | Legal Fees for Arbitration /Portion | Town Legal Service | 2092.5
| 2024-05-14 | 2149 | Town Legal Service | Town Legal Service | 1769
American Arbitration Association | 2024-05-10 | 12078537 | Legal Fees for Arbitration /Portion | Town Legal Service | 186
Shipman & Goodwin | 2024-04-01 | NA | Town Legal Service | Town Legal Service | 11647
Shipman & Goodwin | 2024-08-07 | NA | Town Legal Service | Town Legal Service | 9492.5
Shipman & Goodwin |  | 649884 | Town Legal Service | Town Legal Service | 609
Shipman & Goodwin |  | 2149 | Town Legal Service | Town Legal Service | 551
Shipman & Goodwin |  | 652632 | Town Legal Service | Town Legal Service | 232
Shipman & Goodwin |  |  | Town Legal Service | Town Legal Service | 348
|  |  |  | Total | 31299.5
|  |  | Construction Costs | Construction Manager GMP | 9394309.15
BRD Builders | 2023-03-31 | 1 | Construction Manager GMP | Construction Manager GMP | 182299.77
BRD Builders | 2023-04-30 | 2 | Construction Manager GMP | Construction Manager GMP | 125059.73
BRD Builders | 2023-05-31 | 3 | Construction Manager GMP | Construction Manager GMP | 175505.19
BRD Builders | 2023-06-30 | 4 | Construction Manager GMP | Construction Manager GMP | 148812.75
BRD Builders | 2023-07-31 | 5 | Construction Manager GMP | Construction Manager GMP | 195315.77
BRD Builders | 2023-08-31 | 6 | Construction Manager GMP | Construction Manager GMP | 163575.52
BRD Builders | 2023-09-30 | 7 | Construction Manager GMP | Construction Manager GMP | 150772.51
BRD Builders | 2023-10-31 | 8 | Construction Manager GMP | Construction Manager GMP | 264337.5
BRD Builders | 2023-11-30 | 9 | Construction Manager GMP | Construction Manager GMP | 397627.39
BRD Builders | 2023-12-31 | 10 | Construction Manager GMP | Construction Manager GMP | 671459.95
BRD Builders | 2024-01-31 | 11 | Construction Manager GMP | Construction Manager GMP | 442693.82
BRD Builders | 2024-02-29 | 12 | Construction Manager GMP | Construction Manager GMP | 428279.39
BRD Builders | 2024-03-31 | 13 | Construction Manager GMP | Construction Manager GMP | 268519.42
BRD Builders | 2024-04-30 | 14 | Construction Manager GMP | Construction Manager GMP | 562913.23
BRD Builders | 2024-05-31 | 15 | Construction Manager GMP | Construction Manager GMP | 895896.46
BRD Builders | 2024-06-30 | 16 | Construction Manager GMP | Construction Manager GMP | 406792.06
BRD Builders | 2024-07-31 | 17 | Construction Manager GMP | Construction Manager GMP | 273292.75
BRD Builders | 2024-08-31 | 18 | Construction Manager GMP | Construction Manager GMP | 652703.66
BRD Builders | 2024-09-30 | 19 | Construction Manager GMP | Construction Manager GMP | 1019846.92 | Submitted
BRD Builders | 2024-12-10 | 20 | Construction Manager GMP | Construction Manager GMP | 592005.76
|  |  |  | Total | 8017709.55
|  |  | Owner's Oversight Fees | Testing and Inspections | 40000
IMTL | 2023-05-01 | 5836-A | Owner's Oversight Fees | Testing and Inspections | 1069
IMTL | 2023-06-01 | 5836-B | Owner's Oversight Fees | Testing and Inspections | 4329
IMTL | 2023-07-01 | 5836-C | Owner's Oversight Fees | Testing and Inspections | 5379.94
IMTL | 2023-08-02 | 5836-D | Owner's Oversight Fees | Testing and Inspections | 5555.5
IMTL | 2023-08-07 | 5837-A | Owner's Oversight Fees | Testing and Inspections | 437.5
IMTL | 2023-08-14 | 5837-B | Owner's Oversight Fees | Testing and Inspections | 812.5
IMTL | 2023-09-18 | 5836-E | Owner's Oversight Fees | Testing and Inspections | 1945
IMTL | 2023-09-19 | 5837-C | Owner's Oversight Fees | Testing and Inspections | 500
IMTL | 2023-10-09 | 5826-F (Rev) | Owner's Oversight Fees | Testing and Inspections | 1432
IMTL | 2023-11-17 | 5836-G | Owner's Oversight Fees | Testing and Inspections | 1976.81
IMTL | 2023-11-06 | 5837-D | Owner's Oversight Fees | Testing and Inspections | 500
IMTL | 2023-11-14 | 5837-E | Owner's Oversight Fees | Testing and Inspections | 375
IMTL | 2023-12-14 | 5837-F | Owner's Oversight Fees | Testing and Inspections | 562.5
IMTL | 2024-12-19 | 5836-H | Owner's Oversight Fees | Testing and Inspections | 842
IMTL | 2024-01-11 | 5836-I | Owner's Oversight Fees | Testing and Inspections | 246
IMTL | 2024-01-17 | 5837-G | Owner's Oversight Fees | Testing and Inspections | 687.5
IMTL | 2024-02-06 | 5836-J | Owner's Oversight Fees | Testing and Inspections | 246
IMTL | 2024-03-07 | 5836-K | Owner's Oversight Fees | Testing and Inspections | 246
IMTL | 2024-04-03 | 5836-L | Owner's Oversight Fees | Testing and Inspections | 222
IMTL | 2024-05-31 | 5836-M | Owner's Oversight Fees | Testing and Inspections | 765
IMTL | 2024-05-22 | 5837-H | Owner's Oversight Fees | Testing and Inspections | 625
IMTL | 2024-06-27 | 5863-N (Rev) | Owner's Oversight Fees | Testing and Inspections | 350
IMTL | 2024-08-30 | 5836-O | Owner's Oversight Fees | Testing and Inspections | 1767
IMTL | 2024-09-30 | 5836-P | Owner's Oversight Fees | Testing and Inspections | 1145
IMTL | 2024-10-30 | 5836-Q | Owner's Oversight Fees | Testing and Inspections | 2138
IMTL | 2024-12-10 |  | Owner's Oversight Fees | Testing and Inspections | 1772
|  |  |  | Total | 35926.25
|  |  | Construction Costs | Utility Connection Fees | 81261.86
Eversource (Gas) | 2023-08-23 |  | Gas Service | Utility Connection Fees | 38705.5 | 37205.5
Eversource (Electric) | 2023-11-27 |  | Electric Service | Utility Connection Fees | 7091.26
Colchesetr Water Department | 2023-11-01 |  | Water Connection Fee | Utility Connection Fees | 14460.1
Dutch Associates | 2023-11-01 |  | Easement Documentation | Utility Connection Fees | 3000
Wayne's Tree Service | 2024-04-11 | 16577 | Tree Removal | Utility Connection Fees | 2500
[5 empty] | 21789.82 | Sertex Total
Sertex | 2024-05-15 | 11954 | Fiber line /Conduit Install | Utility Connection Fees | 15505
6284.82
|  |  |  | Total | 81261.86
|  |  | FF & E (Furniture, Fixtures, Equip. | Furniture and Equipment | 298150.6 | FFE Total Committed Cost
Novus | 2024-02-22 | Quote #6254 | Novus Computer Purchase | Furniture and Equipment
Novus | 2024-03-05 | Quote #6285 | Novus Telephone Purchase | Furniture and Equipment
Novus | 2024-03-06 | Quote #6269 | Novus Construction Proposal | Furniture and Equipment
Stategic Spaces | 2024-07-16 |  | Stategic Spaces Proposal | Furniture and Equipment
Total Fitness | 2024-07-16 |  | Total Fitness Proposal | Furniture and Equipment
Novus | 2024-05-03 | Invoice 18763 |  | Furniture and Equipment | 9627.35
Novus | 2024-05-02 | Invoice 18762 |  | Furniture and Equipment | 4802.14
Strategic Spaces | 2024-08-26 | Invoice #1273-30379-0 | Deposit Invoice (8/26/2024) | Furniture and Equipment | 111895.56
Novus | 2024-07-31 | Invoice 19815 |  | Furniture and Equipment | 820
Total Fitness | 2024-10-25 |  | Total Fitness Equipment | Furniture and Equipment | 41038
Sertex | 2024-10-18 | 12366 |  | Misc. | 6284.02
Novus |  | 30054780 - 68416 | FF&E | Furniture & Equipment | 6339.25
Total Fitness |  | 30054780 - 68416 | Fitness Equipment | Fitness Equipment | 5452
|  |  |  | Total | 186258.32
|  |  | Owner's Oversight Fees | Commisioning Agent | 26600
CES | 2024-06-30 | 2024307-001 | Owner's Oversight Fees | Commisioning Agent | 250
CES | 2024-07-31 | 2024307-002 | Owner's Oversight Fees | Commisioning Agent | 1635
CES | 2024-08-31 | 2024307-003 | Owner's Oversight Fees | Commisioning Agent | 3235
CES | 2024-09-30 | 2024307-004 | Owner's Oversight Fees | Commisioning Agent | 1102.5
CES | 2024-10-31 | 2024307-005 | Owner's Oversight Fees | Commisioning Agent | 675
CES | 2024-12-10 |  | Owner's Oversight Fees | Commisioning Agent | 5112.5
|  |  |  | Total | 12010
|  |  |  | Page Total | 9350533.47
|  |  |  | Buget Total | 14104847.03
|  |  |  | Check | -4754313.56

## Tranfers-Adj
Date | Budget Category | Description | Category | Amount
2022-01-11 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -1000
2022-12-01 | Owner's Contingency | Move $$ from Owner's Contingency to GMP | Budget Adjustment | -200000
2023-01-10 | Owner's Contingency | Move $$ from Owner's Contingency to GMP | Budget Adjustment | -200000
2023-08-22 | Owner's Contingency | Move $$ from Owner's Contingency to Utility Connection Fees | Budget Adjustment | -18423
2024-04-09 | Owner's Contingency | Move $$ from Owner's Contingency to Utility Connection Fees | Budget Adjustment | -15000
2024-05-15 | Owner's Contingency | Move $$ from Owner's Contingency to Commisioning Agent | Budget Adjustment | -11600
2024-05-15 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -24000
2024-05-28 | Owner's Contingency | $ Owner Contingency to Town Legal Services | Budget Adjustment | -15000
2024-06-11 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -20000
2024-08-13 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -45000
2024-08-13 | Owner's Contingency | $ Owner Contingency to Town Legal Services | Budget Adjustment | -10000
2024-09-10 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -22000
2024-10-08 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -22000
2024-11-22 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -22000
2024-12-10 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -15097.27
2025-11-04 | Owner's Contingency | $ Owner Contingency to Construction Manager, G<P | Budget Adjustment | -140000
2026-01-27 | Owner's Contingency | $ Owner Contingency to Furniture and Equipment | Budget Adjustment | -20000
2026-03-10 | Owner's Contingency | $ Owner Contingency to Furniture and Equipment | Budget Adjustment | -2000
2026-05-12 | Owner's Contingency | $ Owner Contingency to Furniture and Equipment | Budget Adjustment | -300
| Owner's Contingency |  | Total = | -803420.27
2022-01-11 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 1000
2023-05-09 | Project Manager/Owner's Rep. | $ Utility Conncetion Fee to Project Manager/ Owner Rep | Budget Adjustment | 17000
2024-05-15 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 24000
2024-06-11 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 20000
2024-08-13 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 45000
2024-09-10 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 22000
2024-10-08 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 22000
2024-11-22 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 22000
2024-12-10 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 15097.27
2025-11-04 | Project Manager/Owner's Rep. | $ Project Manager/Owners Rep. to FF&E | Budget Adjustment | -10589.43
| Project Manager/Owner's Rep. |  | Total = | 177507.84
2022-12-01 | Design and Estimating Contingency | Deduct Value/ Move to Utility Connection Fees | Budget Adjustment | -107500
2022-12-01 | Design and Estimating Contingency | Deduct Value/ Move to Construction Manager GMP | Budget Adjustment | -217488
| Design and Estimating Contingency |  | Total = | -324988
2022-10-12 | Utility Connection Fees | Increase value based on BC meeting 10/11/20222 | Budget Adjustment | 107500
2023-01-10 | Utility Connection Fees | Tranfer value to Construction Manager GMP | Budget Adjustment | -40000
2023-03-28 | Utility Connection Fees | Transfer value to AE Fees | Budget Adjustment | -5000
2023-05-09 | Utility Connection Fees | Transfer to Project Manager/ Owner Rep | Budget Adjustment | -17000
2023-05-23 | Utility Connection Fees | Tranfer value to Construction Manager GMP | Budget Adjustment | -40000
2023-08-22 | Utility Connection Fees | Tranfer value from Owner's Contingency | Budget Adjustment | 18423
2024-04-09 | Utility Connection Fees | Tranfer value from Owner's Contingency | Budget Adjustment | 15000
2025-06-17 | Utility Connection Fees | Transfer value to Furniture and Equipment | Budget Adjustment | -2453.32
2025-10-14 | Utility Connection Fees | Transfer value to AE Fees | Budget Adjustment | -6284.82
| Utility Connection Fees |  | Total = | 30184.86
2022-12-01 | Construction Manager GMP | Move remaining value from Design and Estimating Contingency per BC meeting on 10/11/2022 | Budget Adjustment | 217488
2022-12-01 | Construction Manager GMP | Move $$ from State Building Permit | Budget Adjustment | 2017
2022-12-12 | Construction Manager GMP | Value tranferred from Town Insurance/ BR | Budget Adjustment | 12500
2022-12-01 | Construction Manager GMP | Value tranferred from FFE | Budget Adjustment | 200000
2022-12-01 | Construction Manager GMP | Value transferred from Owner Contingency | Budget Adjustment | 200000
2023-01-10 | Construction Manager GMP | Value transferred from AE Fees | Budget Adjustment | 40000
2023-01-10 | Construction Manager GMP | Value transferred from Cost of Issuance | Budget Adjustment | 175000
2023-01-10 | Construction Manager GMP | Value transferred from Admin Costs | Budget Adjustment | 5000
2023-01-10 | Construction Manager GMP | Value transferred from Printing and Legal Notices | Budget Adjustment | 5000
2023-01-10 | Construction Manager GMP | Value transferred from Utility Connection Fees | Budget Adjustment | 40000
2023-01-10 | Construction Manager GMP | Value transferred from Furniture and Equipment | Budget Adjustment | 90000
2023-01-10 | Construction Manager GMP | Value transferred from Moving and Relocation | Budget Adjustment | 15000
2023-01-10 | Construction Manager GMP | Value transferred from Owner Contingency | Budget Adjustment | 200000
2023-05-23 | Construction Manager GMP | Value transferred from Utility Connection Fees | Budget Adjustment | 40000
2023-08-08 | Construction Manager GMP | Value transferred from Moving and Relocation | Budget Adjustment | 5000
2025-11-04 | Construction Manager GMP | Value transferred from Owner Contingency | Budget Adjustment | 140000
2025-11-04 | Construction Manager GMP | Value transferred from Cost of Issuance | Budget Adjustment | 80000
| Construction Manager GMP |  | Total = | 1467005
2022-12-01 | State Building Permit | Remove Value/ Move to GMP | Budget Adjustment | -2017
| State Building Permit |  | Total= | -2017
2022-12-12 | Town Insurance/Builder's Risk | Remove Value/ Move to GMP | Budget Adjustment | -12500
| Town Insurance/Builder's Risk |  | Total= | -12500
2023-07-11 | Testing and Inspections | $ Add Value/ Move from FFE | Budget Adjustment | 10000
2023-10-10 | Testing and Inspections | $ Add Value/ Move from Commisioning Agent | Budget Adjustment | 5000
2025-06-17 | Testing and Inspections | $Removed and added to A/E Fees | Budget Adjustment | -10000
| Testing and Inspections |  | Total= | 5000
2023-01-10 | Architect and Engineering Services | $ from AE Fees to Construction Manager GMP | Budget Adjustment | -40000
2023-03-28 | Architect and Engineering Services | Add Value/ Move from Utility Connection fee | Budget Adjustment | 5000
2025-05-13 | Architect and Engineering Services | Add Value/ Move from Utility Moving & Relocation Costs | Budget Adjustment | 10000
2025-06-17 | Architect and Engineering Services | Add Value/Move from Testing & Inspections | Budget Adjustment | 10000
2025-10-14 | Architect and Engineering Services | Add value/Move from Utility Connection fee | Budget Adjustment | 6284.82
| Architect and Engineering Services |  | Total= | -8715.18
2023-01-10 | Town Professional Fees | $ from Cost of Issuance to Construction Manager GMP | Budget Adjustment | -175000
2025-11-04 | Town Professional Fees | $ from Cost of Issuance to Construction Manager GMP | Budget Adjustment | -80000
| Town Professional Fees |  | Total= | -255000
2023-01-10 | Town Professional Fees | $ from Admin Costs to Concstructoon Manager GMP | Budget Adjustment | -5000
| Town Professional Fees |  | Total= | -5000
2023-01-10 | Town Professional Fees | $ from Printing and Leagl Notices to Construction Manager GMP | Budget Adjustment | -5000
| Town Professional Fees |  | Total= | -5000
2022-12-01 | Furniture and Equipment | $From Furniture and Equipment to Construction Manager - GMP | Budget Adjustment | -200000
2023-01-10 | Furniture and Equipment | $From Furniture and Equipment to Construction Manager - GMP | Budget Adjustment | -90000
2023-07-11 | Furniture and Equipment | $From Furniture and Equipment to Testing & Inspections | Budget Adjustment | -10000
2025-04-08 | Furniture and Equipment | $From Moving & Relocation | Budget Adjustment | 3657.83
2025-05-13 | Furniture and Equipment | $From Moving & Relocation | Budget Adjustment | 2000
2025-06-17 | Furniture and Equipment | $From Utility Connection Fees | Budget Adjustment | 2453.32
2025-06-17 | Furniture and Equipment | $From Moving & Relocation | Budget Adjustment | 6000
2025-11-04 | Furniture and Equipment | $From Project Manager/Owner's Rep. | Budget Adjustment | 10589.43
2026-01-27 | Furniture and Equipment | $From Congingency | Budget Adjustment | 20000
2026-03-20 | Furniture and Equipment | $From Congingency | Budget Adjustment | 2000
2026-05-12 | Furniture and Equipment | $From Congingency | Budget Adjustment | 300
| FF & E (Furniture, Fixtures, Equip. |  | Total= | -252999.42
2023-10-10 | Commisioning Agent | $ from Commisioning Agent to Testing and Inspections | Budget Adjustment | -5000
2024-05-15 | Commisioning Agent | $ from Contingency to Commisioning Agent | Budget Adjustment | 11600
| Commisioning Agent |  | Total= | 6600
2024-05-28 | Town Legal Service | $ Owner Contingency to Town Legal Services | Budget Adjustment | 15000
2024-08-13 | Town Legal Service | $ Owner Contingency to Town Legal Services | Budget Adjustment | 10000
| Town Legal Service |  | Total= | 25000
2023-01-10 | Moving & Relocation Costs | $ from Moving and Relocation Costs to Construction Manager GMP | Budget Adjustment | -15000
2023-08-08 | Moving & Relocation Costs | $ from Moving and Relocation Costs to Construction Manager GMP | Budget Adjustment | -5000
2025-04-08 | Moving & Relocation Costs | $Moving & Relocation Costs to Fixtures Furniture & Equipment | Budget Adjustment | -3657.83
2025-05-13 | Moving & Relocation Costs | $Moving & Relocation Costs to A/E Fees | Budget Adjustment | -10000
2025-05-13 | Moving & Relocation Costs | $Moving & Relocation Costs to Fixtures Furniture & Equipment | Budget Adjustment | -2000
2025-06-17 | Moving & Relocation Costs | $Moving & Relocation Costs to Fixtures Furniture & Equipment | Budget Adjustment | -6000
| Moving & Relocation Costs |  | Total= | -41657.83
|  |  | Math Check | -1.0186e-10