## Budget
|  | Colchester Budget Worksheet For Committee Use |  |  |  |  | 2023-02-13
Munis Acct. No. | Description | Original Budget Amount | Budget Adjustments | Current Budget | Expended (Paid) | Committed Encumbered | Uncommitted Balance | Total Project Cost | % Expended/ Completed
|  | a | b | c | d | e | f | g | h
|  |  |  | a + b |  |  | c - e | e + f | d / c
Architect and Engineering Services
30054780-62201 | A/E Fees | 450000 | -40000 | 410000 | 294166.12 | 402066.12 | 7933.88 | 410000 | 71.75%
Owner's Oversight Fees
30054780-62250 | Project Manager/Owner's Rep. | 297000 | 1000 | 298000 | 53615.25 | 297405.14 | 594.86 | 298000 | 17.99%
30054780-62208 | Commissioning Agent | 12500 | 0 | 12500 | 0 | 0 | 12500 | 12500 | 0%
30054780-62208 | Testing and Inspections | 10000 | 0 | 10000 | 0 | 0 | 10000 | 10000 | 0%
Town Professional Fees
30054780-60302 | Town Legal Services | 5000 | 0 | 5000 | 0 | 940.5 | 4059.5 | 5000 | 0%
30054780-61101 | Costs of Issuance | 178107 | -175000 | 3107 | 0 | 0 | 3107 | 3107 | 0%
30054780-61206 | Town Insurance/Builder's Risk | 12500 | -12500 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-61105 | Administrative Costs | 12000 | -5000 | 7000 | 1540 | 1540 | 5460 | 7000 | 22%
30054780-61232 | Printing & Legal Notices | 8000 | -5000 | 3000 | 725.62 | 725.62 | 2274.38 | 3000 | 24.19%
Construction Costs
30054780-64469 | Construction Manager GMP | 7429465 | 1202005 | 8631470 | 0 | 8625000 | 6470 | 8631470 | 0%
30054780-64469 | State Building Permit | 2017 | -2017 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-64469 | Utility Connection Fees | 15000 | 67500 | 82500 | 0 | 0 | 82500 | 82500 | 0%
FF & E (Furniture, Fixtures, Equip.
30054780-68416 | Furniture and Equipment | 300000 | -290000 | 10000 | 0 | 0 | 10000 | 10000 | 0%
30054780-61263 | Moving & Relocation Costs | 20000 | -15000 | 5000 | 0 | 0 | 5000 | 5000 | 0%
Contingencies
30054780-61411 | Design and Estimating Contingency | 324988 | -324988 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-61411 | Owner's Contingency | 423423 | -401000 | 22423 | 0 | 0 | 22423 | 22423 | 0%
| Grand Totals | 9500000 | 0 | 9500000 | 350046.99 | 9327677.38 | 172322.62 | 9500000 | 3.685%
Pre Referendum Costs
| Silver/Petrucelli - Architects | 47000 | 0 | 47000 | 41352.08 | 46991 | 9 | 47000 | 87.98%
| Construction Solutions Group - OPM | 15000 | 0 | 15000 | 14798.65 | 14798.65 | 201.35 | 15000 | 98.66%
| Pre Referendum Totals | 62000 | 0 | 62000 | 56150.73 | 61789.65 | 210.35 | 62000 | 90.57%
COR's
Silver/Petrucelli
001 | Additional Test Bore Costs | a: 2022-03-08; c: 5472; e: 5472
002 | Flow Test and Boring Survey | a: 2022-05-02; c: 3955.12; e: 3955.12
003 | Wetlands Delineation/ Wetlands Report & Submission | a: 2022-05-24; c: 8030; e: 8030
004
005 | Fee Adjustment | a: 2022-06-28; c: 485; e: 485
006
Construction Solutions Group
001 | Additional Cost Estimates | a: 2022-01-11; c: 15455; e: 15455
002
003
004
005
006

## Adjustments
Date | Budget Category | Description | Category | Amount
2022-01-11 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -1000
2022-12-12 | Owner's Contingency | Move $$ from Owner's Contingency to GMP | Budget Adjustment | -200000
| Owner's Contingency |  | Total = | -201000
2022-01-11 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 1000
| Project Manager/Owner's Rep. |  | Total = | 1000
2022-10-12 | Design and Estimating Contingency | Deduct Value/ Move to Utility Connection Fees |  | -107500
2022-10-12 | Design and Estimating Contingency | Deduct Value/ Move to Construction Manager GMP |  | -217488
| Design and Estimating Contingency |  | Total = | -324988
2022-10-12 | Utility Connection Fees | Increase value based on BC meeting 10/11/20222 |  | 107500
| Utility Connection Fees |  | Total = | 107500
2022-10-12 | Construction Manager GMP | Move remaining value from Design and Estimating Contingency per BC meeting on 10/11/2022 |  | 217488
2022-10-23 | Construction Manager GMP | Move $$ from State Building Permit |  | 2017
2022-12-12 | Construction Manager GMP | Value tranferred from Town Insurance/ BR |  | 12500
2022-12-12 | Construction Manager GMP | Value tranferred from FFE |  | 200000
2022-12-12 | Construction Manager GMP | Value transferred from Owner Contingency |  | 200000
2022-12-12 | Construction Manager GMP | Bendas Gift Added to Budget |  | 575000
| Construction Manager GMP |  | Total = | 1207005
2022-10-23 | State Building Permit | Remove Value/ Move to GMP |  | -2017
| State Building Permit |  | Total= | -2017
2022-12-12 | Town Insurance/Builder's Risk | Remove Value/ Move to GMP |  | -12500
| Town Insurance/Builder's Risk |  | Total= | -12500
2022-12-12 | FFE
|  | Remove Value/ Move to GMP |  | -200000
|  |  | Total= | -200000

## Payments
Firm Name | Date | Invoice Number | Description | Category | Amount
CSG |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 14798.65
CSG | 2021-03-04 | 1 | Pre-Construction Services | Pre Referendum Costs | 9000
CSG | 2021-06-07 | 2 | Pre-Construction Services | Pre Referendum Costs | 3000
CSG | 2021-07-23 | 3 | Pre-Construction Services | Pre Referendum Costs | 2798.65
|  |  |  | Total | 14798.65
CSG |  |  | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 281950.14
CSG | 2022-03-01 | 4 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6880
CSG | 2022-04-01 | 5 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6000
CSG | 2022-05-01 | 6 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 14525
CSG | 2022-06-01 | 7 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 2000
CSG | 2022-07-03 | 7A | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6050
CSG | 2022-08-01 | 8 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 15132.69
CSG | 2022-11-30 | 9 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 3027.56
|  |  |  | Total | 53615.25
Committee Clerk |  |  | Administrative Costs | Administrative Costs | 0
Committee Clerk | 2021-12-14 | 1 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-01-25 | 2 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-08 | 3 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-22 | 4 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-08 | 5 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-29 | 6 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-12 | 7 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-26 | 8 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-10 | 9 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-24 | 10 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-14 | 11 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-28 | 12 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-12 | 13 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-26 | 14 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-01 | 15 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-09 | 16 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-23 | 17 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-09-13 | 18 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-19 | 19 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-25 | 20 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-11-22 | 21 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-12-01 | 22 | Administrative Costs | Administrative Costs | 70
|  |  |  | Total | 1540
Silver Petrucelli |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 46991
Silver Petrucelli | 2020-06-01 | 20-1473 | Silver/Petrucelli - Architects | Pre Referendum Costs | 9398
Silver Petrucelli | 2020-07-01 | 20-1694 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2020-08-01 | 20-1943 | Silver/Petrucelli - Architects | Pre Referendum Costs | 2349.55
Silver Petrucelli | 2020-09-01 | 20-2176 | Silver/Petrucelli - Architects | Pre Referendum Costs | 14097.3
Silver Petrucelli | 2020-10-01 | 20-2257 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2021-02-01 | 21-0420 | Silver/Petrucelli - Architects | Pre Referendum Costs | 1409.93
|  |  |  | Total | 41352.08
Silver Petrucelli |  |  | Architect and Engineering Services | A/E Fees | 384124
Silver Petrucelli | 2022-02-01 | 22-0125 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-03-01 | 22-0208 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-04-01 | 22-0366 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-05-01 |  | Architect and Engineering Services | A/E Fees | 7553
Silver Petrucelli | 2022-06-01 | 22-0537 | Architect and Engineering Services | A/E Fees | 48986.6
Silver Petrucelli | 2022-06-01 | 22-0637 | Architect and Engineering Services | A/E Fees | 11985.12
Silver Petrucelli | 2022-07-01 | 22-0703 | Architect and Engineering Services | A/E Fees | 42211.4
Silver Petrucelli | 2022-08-01 | 22-0905 | Architect and Engineering Services | A/E Fees | 20716.8
Silver Petrucelli | 2022-09-01 | 22-0987 | Architect and Engineering Services | A/E Fees | 5179.2
Silver Petrucelli | 2022-10-01 | 22-1157 | Architect and Engineering Services | A/E Fees | 17264
|  | 22-1283 | Architect and Engineering Services | A/E Fees | 4316
|  |  |  | Total | 294166.12
|  |  | Printing & Legal Notices | Printing & Legal Notices
Rivereast News Bulletin | 2022-09-07 | 217798-001RE | Printing & Legal Notices | Printing & Legal Notices | 220
Hartford Courant | 2022-09-11 | 60181913000 | Printing & Legal Notices | Printing & Legal Notices | 505.62
|  |  |  | Total | 725.62
|  |  | Town Legal Services | Town Legal Service
Shipman & Goodwin | 2022-02-16 | 1213 | Town Legal Service | Town Legal Service | 940.5
|  |  |  | Total | 940.5