## Budget
|  | Colchester Budget |  |  |  |  | Date: 8.12.2023
Munis Acct. No. | Description | Original Budget Amount | Budget Adjustments | Current Budget | Expended (Invoiced) | Committed Encumbered | Uncommitted Balance | Total Project Cost | % Expended/ Completed
|  | a | b | c | d | e | f | g | h
|  |  |  | a + b |  |  | c - e | e + f | d / c
Architect and Engineering Services
30054780-62201 | A/E Fees | 450000 | -35000 | 415000 | 336091.49 | 411621.49 | 3378.51 | 415000 | 80.99%
Owner's Oversight Fees
30054780-62250 | Project Manager/Owner's Rep. | 297000 | 18000 | 315000 | 141468.86 | 314175.14 | 824.86 | 315000 | 44.91%
30054780-62208 | Commissioning Agent | 12500 | 0 | 12500 | 0 | 0 | 12500 | 12500 | 0%
30054780-62208 | Testing and Inspections | 10000 | 10000 | 20000 | 16333.44 | 20000 | 0 | 20000 | 81.67%
Town Professional Fees
30054780-60302 | Town Legal Services | 5000 | 0 | 5000 | 940.5 | 940.5 | 4059.5 | 5000 | 18.81%
30054780-61101 | Costs of Issuance | 178107 | -175000 | 3107 | 0 | 0 | 3107 | 3107 | 0%
30054780-61206 | Town Insurance/Builder's Risk | 12500 | -12500 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-61105 | Administrative Costs | 12000 | -5000 | 7000 | 2520 | 2520 | 4480 | 7000 | 36%
30054780-61232 | Printing & Legal Notices | 8000 | -5000 | 3000 | 725.62 | 725.62 | 2274.38 | 3000 | 24.19%
Construction Costs
30054780-64469 | Construction Manager GMP | 7429465 | 1247005 | 8681470 | 631677.44 | 8672115.12 | 9354.88 | 8681470 | 7.276%
30054780-64469 | State Building Permit | 2017 | -2017 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-64469 | Utility Connection Fees | 15000 | 5500 | 20500 | 0 | 0 | 20500 | 20500 | 0%
FF & E (Furniture, Fixtures, Equip.
30054780-68416 | Furniture and Equipment | 300000 | -300000 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-61263 | Moving & Relocation Costs | 20000 | -20000 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Contingencies
30054780-61411 | Design and Estimating Contingency | 324988 | -324988 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
30054780-61411 | Owner's Contingency | 423423 | -401000 | 22423 | 0 | 0 | 22423 | 22423 | 0%
| Grand Totals | 9500000 | 0 | 9500000 | 1129757.35 | 9422097.87 | 77902.13 | 9500000 | 11.89%
Pre Referendum Costs
| Silver/Petrucelli - Architects | 47000 | 0 | 47000 | 41352.08 | 46991 | 9 | 47000 | 87.98%
| Construction Solutions Group - OPM | 15000 | 0 | 15000 | 14798.65 | 14798.65 | 201.35 | 15000 | 98.66%
| Pre Referendum Totals | 62000 | 0 | 62000 | 56150.73 | 61789.65 | 210.35 | 62000 | 90.57%
COR's
Silver/Petrucelli
001 | Additional Test Bore Costs | a: 2022-03-08; e: 5472
002 | Additional Survey | a: 2022-06-17; e: 3300
003 | Wetlands Delineation/ Wetlands Report & Submission | a: 2022-06-17; e: 8030
004 | Soil Boring and Flow Test | a: 2022-06-17; e: 655.12
005 | Fee Adjustment | a: 2022-06-27; e: 485
006 | Printing Reimbursible | a: 2023-03-08; e: 2955.37
007 | Escalation Costs | a: 2023-03-28; e: 6600
Total |  | e: 27497.49
Construction Solutions Group
001 | Additional Cost Estimates | a: 2022-01-11; e: 15455
002 | Escalation Costs | a: 2023-05-09; e: 16770
003
004
005
006
Total |  | e: 32225
BRD Builders |  | f: Pending
001 | Siltsoxx - Credit | a: 2023-04-19; e: -3403.07
002 | Stone Trenches | a: 2023-05-09; e: 45270.52
003 | Conduit for future generator | a: 2023-06-15; f: 14346.35
004 | Foundation Building Code Upgardes | e: 18384.74
005 | Storefront Credit (CW-1 Elleptical) | e: -13136.46
006
Total |  | e: 47115.73

## Payments- Inv
Firm Name | Date | Invoice Number | Description | Category | Amount
CSG |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 14798.65
CSG | 2021-03-04 | 1 | Pre-Construction Services | Pre Referendum Costs | 9000
CSG | 2021-06-07 | 2 | Pre-Construction Services | Pre Referendum Costs | 3000
CSG | 2021-07-23 | 3 | Pre-Construction Services | Pre Referendum Costs | 2798.65
|  |  |  | Total | 14798.65
CSG |  |  | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 281950.14
CSG | 2022-03-01 | 4 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6880
CSG | 2022-04-01 | 5 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6000
CSG | 2022-05-01 | 6 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 14525
CSG | 2022-06-01 | 7 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 2000
CSG | 2022-07-03 | 7A | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 6050
CSG | 2022-08-01 | 8 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 15132.69
CSG | 2022-11-30 | 9 | Construction Services -Post Referendum | Project Manager/Owner's Rep. | 3027.56
CSG | 2023-05-02 | 1a | Construction Services -CA | Project Manager/Owner's Rep. | 20819.99
CSG | 2023-06-06 | 2a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
CSG | 2023-07-07 | 3a | Construction Services -CA | Project Manager/Owner's Rep. | 22344.54
|  |  |  | Total | 119124.32
Committee Clerk |  |  | Administrative Costs | Administrative Costs | 0
Committee Clerk | 2021-12-14 | 1 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-01-25 | 2 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-08 | 3 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-02-22 | 4 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-08 | 5 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-03-29 | 6 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-12 | 7 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-04-26 | 8 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-10 | 9 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-05-24 | 10 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-14 | 11 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-06-28 | 12 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-12 | 13 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-07-26 | 14 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-01 | 15 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-09 | 16 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-08-23 | 17 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-09-13 | 18 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-19 | 19 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-10-25 | 20 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-11-22 | 21 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-12-01 | 22 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 23 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 24 | Administrative Costs | Administrative Costs | 70
Committee Clerk |  | 25 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2022-12-13 | D- 011 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-01-10 | D- 012 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-01-24 | D- 013 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-02-14 | D- 014 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-02-28 | D- 015 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-03-28 | D- 016 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-04-04 | D- 017 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-04-11 | D- 018 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-05-09 | D- 019 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-05-23 | D- 020 | Administrative Costs | Administrative Costs | 70
Committee Clerk | 2023-06-13 | D- 021 | Administrative Costs | Administrative Costs | 70
|  |  |  | Total | 2520
Silver Petrucelli |  |  | Pre-Construction Services Contract Value | Pre Referendum Costs | 46991
Silver Petrucelli | 2020-06-01 | 20-1473 | Silver/Petrucelli - Architects | Pre Referendum Costs | 9398
Silver Petrucelli | 2020-07-01 | 20-1694 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2020-08-01 | 20-1943 | Silver/Petrucelli - Architects | Pre Referendum Costs | 2349.55
Silver Petrucelli | 2020-09-01 | 20-2176 | Silver/Petrucelli - Architects | Pre Referendum Costs | 14097.3
Silver Petrucelli | 2020-10-01 | 20-2257 | Silver/Petrucelli - Architects | Pre Referendum Costs | 7048.65
Silver Petrucelli | 2021-02-01 | 21-0420 | Silver/Petrucelli - Architects | Pre Referendum Costs | 1409.93
|  |  |  | Total | 41352.08
Silver Petrucelli |  |  | Architect and Engineering Services | A/E Fees | 384124
Silver Petrucelli | 2022-02-01 | 22-0125 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-02-01 | 22-0036 | Architect and Engineering Services | A/E Fees | 0
Silver Petrucelli | 2022-03-01 | 22-0208 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-04-01 | 22-0366 | Architect and Engineering Services | A/E Fees | 45318
Silver Petrucelli | 2022-05-01 | 22-0432 | Architect and Engineering Services | A/E Fees | 7553
Silver Petrucelli | 2022-06-01 | 22-0537 | Architect and Engineering Services | A/E Fees | 48986.6
Silver Petrucelli | 2022-06-01 | 22-0637 | Architect and Engineering Services | A/E Fees | 11985.12
Silver Petrucelli | 2022-07-01 | 22-0703 | Architect and Engineering Services | A/E Fees | 42211.4
Silver Petrucelli | 2022-08-01 | 22-0905 | Architect and Engineering Services | A/E Fees | 20716.8
Silver Petrucelli | 2022-09-01 | 22-0987 | Architect and Engineering Services | A/E Fees | 5179.2
Silver Petrucelli | 2022-10-01 | 22-1157 | Architect and Engineering Services | A/E Fees | 17264
Silver Petrucelli | 2022-11-01 | 22-1283 | Architect and Engineering Services | A/E Fees | 4316
Silver Petrucelli | 2023-02-01 | 22-0232 | Architect and Engineering Services | A/E Fees | 1079
Silver Petrucelli | 2023-02-01 | 22-0281 | Architect and Engineering Services | A/E Fees | 2955.37
Silver Petrucelli | 2023-03-01 | 23-166 | Architect and Engineering Services | A/E Fees | 1079
Silver Petrucelli | 2023-04-01 | 23-224 | Architect and Engineering Services | A/E Fees | 11995
Silver Petrucelli | 2023-05-01 | 23-403 | Architect and Engineering Services | A/E Fees | 7553
Silver Petrucelli | 2023-06-01 | 23-557 | Architect and Engineering Services | A/E Fees | 6474
|  |  |  | Total | 325301.49
|  |  | Printing & Legal Notices | Printing & Legal Notices
Rivereast News Bulletin | 2022-09-07 | 217798-001RE | Printing & Legal Notices | Printing & Legal Notices | 220
Hartford Courant | 2022-09-11 | 60181913000 | Printing & Legal Notices | Printing & Legal Notices | 505.62
|  |  |  | Total | 725.62
|  |  | Town Legal Services | Town Legal Service
Shipman & Goodwin | 2022-02-16 | 1213 | Town Legal Service | Town Legal Service | 940.5
|  |  |  | Total | 940.5
|  |  | Construction Costs | Construction Manager GMP
BRD Builders |  | 1 | Construction Manager GMP | Construction Manager GMP | 182299.77
|  | 2 | Construction Manager GMP | Construction Manager GMP | 125059.73
|  | 3 | Construction Manager GMP | Construction Manager GMP | 175505.19
|  | 4 | Construction Manager GMP | Construction Manager GMP | in review
|  | 4 | Construction Manager GMP | Construction Manager GMP | in review
|  |  |  | Total | 482864.69
|  |  | Owner's Oversight Fees | Testing and Inspections | 10000
IMTL | 2023-05-01 | 5836-A | Owner's Oversight Fees | Testing and Inspections | 1069
IMTL | 2023-06-01 | 5836-B | Owner's Oversight Fees | Testing and Inspections | 4329
IMTL | 2023-07-01 | 5836-C | Owner's Oversight Fees | Testing and Inspections | 5379.94
|  |  |  | Total | 10777.94
|  |  |  | Page Total | 998405.29
|  |  |  | Buget Total | 1185908.08
|  |  |  | Check | -187502.79

## Tranfers-Adj
Date | Budget Category | Description | Category | Amount
2022-01-11 | Owner's Contingency | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | -1000
2022-12-01 | Owner's Contingency | Move $$ from Owner's Contingency to GMP | Budget Adjustment | -200000
2023-01-10 | Owner's Contingency | Move $$ from Owner's Contingency to GMP | Budget Adjustment | -200000
| Owner's Contingency |  | Total = | -401000
2022-01-11 | Project Manager/Owner's Rep. | $ Owner Contingency to Project Manager/ Owner's Rep | Budget Adjustment | 1000
2023-05-09 | Project Manager/Owner's Rep. | $ Utility Conncetion Fee to Project Manager/ Owner Rep | b | 17000
| Project Manager/Owner's Rep. |  | Total = | 18000
2022-12-01 | Design and Estimating Contingency | Deduct Value/ Move to Utility Connection Fees | Budget Adjustment | -107500
2022-12-01 | Design and Estimating Contingency | Deduct Value/ Move to Construction Manager GMP | Budget Adjustment | -217488
| Design and Estimating Contingency |  | Total = | -324988
2022-10-12 | Utility Connection Fees | Increase value based on BC meeting 10/11/20222 | Budget Adjustment | 107500
2023-01-10 | Utility Connection Fees | Tranfer value to Construction Manager GMP | Budget Adjustment | -40000
2023-03-28 | Utility Connection Fees | Transfer value to AE Fees | Budget Adjustment | -5000
2023-05-09 | Utility Connection Fees | Transfer to Project Manager/ Owner Rep | Budget Adjustment | -17000
2023-05-23 | Utility Connection Fees | Tranfer value to Construction Manager GMP | Budget Adjustment | -40000
| Utility Connection Fees |  | Total = | 5500
2022-12-01 | Construction Manager GMP | Move remaining value from Design and Estimating Contingency per BC meeting on 10/11/2022 | Budget Adjustment | 217488
2022-12-01 | Construction Manager GMP | Move $$ from State Building Permit | Budget Adjustment | 2017
2022-12-01 | Construction Manager GMP | Value tranferred from Town Insurance/ BR | Budget Adjustment | 12500
2022-12-01 | Construction Manager GMP | Value tranferred from FFE | Budget Adjustment | 200000
2022-12-01 | Construction Manager GMP | Value transferred from Owner Contingency | Budget Adjustment | 200000
2023-01-10 | Construction Manager GMP | Value transferred from AE Fees | Budget Adjustment | 40000
2023-01-10 | Construction Manager GMP | Value transferred from Cost of Insurnace | Budget Adjustment | 175000
2023-01-10 | Construction Manager GMP | Value transferred from Admin Costs | Budget Adjustment | 5000
2023-01-10 | Construction Manager GMP | Value transferred from Printing and Legal Notices | Budget Adjustment | 5000
2023-01-10 | Construction Manager GMP | Value transferred from Utility Connection Fees | Budget Adjustment | 40000
2023-01-10 | Construction Manager GMP | Value transferred from Furniture and Equipment | Budget Adjustment | 90000
2023-01-10 | Construction Manager GMP | Value transferred from Moving and Relocation | Budget Adjustment | 15000
2023-01-10 | Construction Manager GMP | Value transferred from Owner Contingency | Budget Adjustment | 200000
2023-05-23 | Construction Manager GMP | Value transferred from Utility Connection Fees | Budget Adjustment | 40000
2023-08-08 | Construction Manager GMP | Value transferred from Moving and Relocation | Budget Adjustment | 5000
| Construction Manager GMP |  | Total = | 1247005
2022-12-01 | State Building Permit | Remove Value/ Move to GMP | Budget Adjustment | -2017
| State Building Permit |  | Total= | -2017
2022-12-12 | Town Insurance/Builder's Risk | Remove Value/ Move to GMP | Budget Adjustment | -12500
| Town Insurance/Builder's Risk |  | Total= | -12500
2022-12-01 | FFE | Remove Value/ Move to GMP | Budget Adjustment | -200000
2023-01-10 | FFE | Remove Value | Budget Adjustment | -90000
2023-07-11 | FFE | Remove Value/ Move to Testing and Inspections | Budget Adjustment | -10000
| FFE |  | Total= | -300000
2023-07-11 | Testing and Inspections | $ Add Value/ Move from FFE | Budget Adjustment | 10000
| Testing and Inspections |  | Total= | 10000
2023-01-10 | Architect and Engineering Services | $ from AE Fees to Construction Manager GMP | Budget Adjustment | -40000
2023-03-28 | Architect and Engineering Services | Add Value/ Move from Utility Connection fee | Budget Adjustment | 5000
| Architect and Engineering Services |  | Total= | -35000
2023-01-10 | Town Professional Fees | $ from Cost of Insurance to Construction Manager GMP | Budget Adjustment | -175000
| Town Professional Fees |  | Total= | -175000
2023-01-10 | Town Professional Fees | $ from Admin Costs to Concstructoon Manager GMP | Budget Adjustment | -5000
| Town Professional Fees |  | Total= | -5000
2023-01-10 | Town Professional Fees | $ from Printing and Leagl Notices to Construction Manager GMP | Budget Adjustment | -5000
| Town Professional Fees |  | Total= | -5000
2023-01-10 | Moving and Relocation Costs | $ from Moving and Relocation Costs to Construction Manager GMP | Budget Adjustment | -15000
2023-08-08 | Moving and Relocation Costs | $ from Moving and Relocation Costs to Construction Manager GMP Budget Adjustment |  | -5000
| Moving and Relocation Costs |  | Total= | -20000
|  |  | Math Check | 0